## Slide 1: Kaizen (Lean Event)
Chapter 2

## Slide 2: Kaizen
Team effort dedicated to implementing lean tools and concepts in a targeted area.
Involves process “insiders”, plus anyone else who has something to offer—“outsiders” or “fresh eyes”.
A completely unique event. No two lean events are alike.

## Slide 3: Kaizen: Purpose
Evaluate the current situation
Identify areas of opportunity
Modify existing process
Implement new standard work
Conclude with a final presentation to senior management
Emphasis is on doing something, to get going.

## Slide 4: Plan the Lean Event
Scope
States where and on what will the team focus its efforts. Describes what is and is not be included.
Must focus on the process customer.
  Considers the value stream from customer’s point of view
Must be realistic, challenging, but not too aggressive. Must be attainable.

## Slide 5: Plan
Dates
Time during which event is to occur (usually 3-5 days)
Consider availability of team members, team leaders, consultant, etc.
Avoid times of excessively high volume

## Slide 6: Plan
Objectives
SMART
  Specific
  Measurable
  Attainable
  Realistic
  Time bound.
Focus on getting things done!
  Use “stretch” objectives: create sense of urgency to generate dramatic improvements.
If an objective proves unrealistic and cannot be accomplished in the event, put it on the to-do list with a date to revisit it.

## Slide 7: Plan
Team leader
Fully committed to the success of the event
Traits: organization, communication, leadership, bias for getting things done.
Responsible to team members and top management

## Slide 8: Plan
Team Members
Must understand and accept responsibility.
  Requires time, effort, and full engagement
  No slackers!
  If unable to devote necessary time, can be included as ad-hoc members.
Must have
  Skills: competency to understand the process and make changes
  Cross-functional representation: all departments involved in the process and influenced by it must be represented.
  Fresh eyes: people unfamiliar with an area have a unique perspective and see problems or suggest solutions other would miss.

## Slide 9: Plan
Notify management and especially to areas directly or indirectly affected by the changes.
Notify services such as maintenance, IT, environmental services, purchasing, finance, safety, and infection control about dates and likely need for support.
Train team members beforehand in lean concepts
Set aside a meeting place (“war room”) to meet, brainstorm, work, and eat.
  Will need standard work forms, markers, overhead, LCD projector, flip charts, table, chairs, etc.

## Slide 10: Provide Information
Prior to event,
  Provide team members with as much information as possible about the target process.
  Use information to become familiar with the process before the event begins .
Information for analysis must be current and obtained during the event through measurement and observation.
  Information supplied before the event is not used to analyze the process or make decisions.

## Slide 11: Kick off (add Charter)
Kick off initiated by a senior administrator
  Explain linkage between the event and strategic plans
  Emphasize organization’s commitment to the effort.
Describe upcoming steps of event and procedure for the process walk-through

## Slide 12
The Charter
xxx
SS

## Slide 13: Conduct Event

## Slide 14: Visit target area (Gemba)
Divide team into two groups: one to ask questions, other to record answers.
Team visits area designated for improvement, walks through process step-by-step and documents it.
Look at both physical and information flows.
Notes: <number>

## Slide 15: Map the Process
Transfer data to value stream maps, process maps, time observation sheets, standard work sheets, etc.
Post on the “war room” walls.

## Slide 16
Event steps
  First day: Completely document and map the process
  Subsequent days: Identify wastes and opportunities, generate ideas, begin to implement lean tools, verify results
  Final day: tie up loose ends, verify and quantify results, develop standard work methods, give final presentation

## Slide 17: Final Presentation
Every team member participates
Introductions—team members introduce selves
Objectives—what the team was trying to accomplish
Situation before event—problems and opportunities.
  Show data and process steps before improvement.
Accomplishments—changes implemented during event.
  Steps that eliminated non-value-added: implementation of lean tools—standard work, kanban, mistake-proofing, quick changeover, visual control, etc.

## Slide 18: Final Presentation
Situation after event—what the new process looks like and new standard work forms.
Results versus objectives.
  Okay if only achieved, say, 30% improvement when objective was 50%.
Improvement to-do list (parking lot)—everything the team was not able to accomplish.
  Explain next steps, who responsible, expected results and completion dates.
Ideally the presentation is attended by all senior managers.

## Slide 19: To Be Done
What | When | Who
Install communication link between Soiled/Clean Rooms and SRP | Waiting on approval | Brad, Jon
Determine if OR Room 8 Trays are Trauma Only | ASAP | Management
Train OR Ortho Team and SST’s on OR Room Std Work and OR Room 8 Kanban/Std Work | Wednesday 3/17 | Carmen, Jose, Greg, Debbie
Implement OR Ortho Team on OR Room Std Work and OR Room 8 Kanban/Std Work | Monday 3/22 | OR, SRP, Greg
Kaizen | When
5S/Std Work Opex Tray Process | TBD
Std Work -Preference Cards (by svc line) | TBD
JDI – Tray/Instrument Photos | TBD
5S - Soiled Utility Room | TBD
Kanban/Std Work – Case Cart | TBD
Greg

## Slide 20: PDCA and Kaizen
1. Plan kaizen event
2. Do kaizen event
3. Check results daily (MDI—
Manage Daily Improvement)
4. Act: Sustain, revisit, redo