Chapter 6: The Work Breakdown Structure and Project Estimation

True/False

- A work breakdown structure (WBS) represents a logical decomposition of the work to be performed and how the product, service, or result is naturally subdivided.

  - True

  - False

True

- The work breakdown structure (WBS) decomposes, or subdivides, the project into smaller components and more manageable units of work called work packages.

  - True

  - False

True

- A tangible and verifiable piece of work is called a milestone.

  - True

  - False

False

- Each phase of the project should provide at least one specific deliverable.

  - True

  - False

True

- The 100 percent rule is the most important criterion in the developing and evaluating the WBS. The rule states: “The (parent) element must represent 100 percent of the work applicable to next level decomposition of a WBS element (child level).”

  - True

  - False

False

- In much the same fashion as the claim “you can never be too rich”, when developing a WBS, one can never have too much detail in planning activities.

  - True

  - False

False

- One way to ensure that the WBS has the appropriate level of detail is to ensure that the people who do the work are involved in its development.

  - True

  - False

True

- The most common error in guesstimating is to be pessimistic and to overestimate the time and resources necessary to complete a project.

  - True

  - False

False

- The Delphi technique is a quick and economical way to estimate the duration and costs of project activities.

  - True

  - False

False

- Time boxing involves allocating a time segment for a task rather than attempting to estimate how long that task should take.

  - True

  - False

True

- According to the text, most real-world estimating is made using top-down estimating.

  - True

  - False

False

- Basing an estimate of activity durations on experience gained from working on similar projects is called analogous estimation.

  - True

  - False

True

- Software engineering refers to a broad range of measurements for objectively evaluating computer software.

  - True

  - False

False

- The three major factors in estimating an IT application are: size, complexity, and constraints & influencers.

  - True

  - False

True

- Counting lines of code (LOC) is a good way to encourage efficient programming.

  - True

  - False

False

- Because function points are independent of technology, they provide a way to compare projects that may use different platforms or languages.

  - True

  - False

True

- COCOMO is an example of a non-parametric model because it is characterized by a usually unlimited set of named parameters.

  - True

  - False

False

- The use of heuristics is based following immutable principles of project development and lead to highly accurate forecasts.

  - True

  - False

False

- Research suggests that projects that use a formal estimating tool have a better chance of delivering a system that is on time and within budget.

  - True

  - False

True

- If the estimates from different estimating techniques are fairly close, then you can average them with a fairly high degree of confidence.

  - True

  - False

True

Multiple Choice

- The PMBOK® area called project time management includes all of the following except:

a)  Activity definition

b)  Activity assignment

c)  Activity duration estimation

d)  Schedule development

e)  Schedule control

Answer: B

- Which of the following statements about the work breakdown structure (WBS) is not true?

a)  The WBS provides a hierarchical structure that outlines the activities or work that needs to be done in order to complete the project scope.

b)  The WBS should support the project's MOV

c)  The WBS should be developed by the project manager.

d)  The WBS provides a framework for developing a tactical plan to structure the project work.

e)  The WBS provides a bridge or link between the project’s scope and the detailed project plan

Answer: C

3.	The Work Breakdown Structure is subdivided into smaller components called:

a)  work packages

b)  milestones

c)  deliverables

d)  tasks

e)  activities

Answer: A

4.	In the WBS context, a crux is best described by which of the following:

a)  a risk metric

b)  a phase gate

c)  evidence of a phase completion

d)  a deliverable

e)  a proof of concept

Answer: E

5.  An estimation technique characterized by schedule and cost estimates of how long something should take or should cost.

a)  Guesstimating

b)  Delphi Technique

c)  Time Boxing

d)  Top-Down Estimating

e)  Bottom-Up Estimating

Answer: D

6.  An estimation technique characterized by the dividing the project into smaller modules and then directly estimating the time and effort in terms of person-hours, person-weeks, or person-months for each module best describes

a)  Guesstimating

b)  Delphi Technique

c)  Time Boxing

d)  Top-Down Estimating

e)  Bottom-Up Estimating

Answer: E

7.  An estimation technique characterized by picking numbers out of the air or "ballparking".

a)  Guesstimating

b)  Delphi Technique

c)  Time Boxing

d)  Top-Down Estimating

e)  Bottom-Up Estimating

Answer: A

8.	An estimation technique characterized by the allocation of a timeframe for a specified activity. e.g. a team has two weeks to complete a task and at the end of two weeks work on that task ceases.

a)  Guesstimating

b)  Delphi Technique

c)  Time Boxing

d)  Top-Down Estimating

e)  Bottom-Up Estimating

Answer: C

9.	An estimation technique characterized by the recruitment of multiple experts who provide rounds of estimates until a consensus estimate emerges.

a)  Guesstimating

b)  Delphi Technique

c)  Time Boxing

d)  Top-Down Estimating

e)  Bottom-Up Estimating

Answer: B

10.	An entity in an Entity-Relationship Diagram (ERD) would be considered an:

a)  Internal Logical File (ILF)

b)  External Interface File (EIF)

c)  External Input (EI)

d)  External Output (EO)

e)  External Inquiry (EQ)

Answer: A

11.	A screen that allows the user to input information using a keyboard and a mouse would be called an:

a)  Internal Logical File (ILF)

b)  External Interface File (EIF)

c)  External Input (EI)

d)  External Output (EO)

e)  External Inquiry (EQ)

Answer: C

12.	An entity or data set that includes customer names and addresses that  is maintained by another application system would be called an:

a)  Internal Logical File (ILF)

b)  External Interface File (EIF)

c)  External Input process (EI)

d)  External Output (EO)

e)  External Inquiry (EQ)

Answer: B

13.	A management report and its accompanying graphs would be considered an:

a)  Internal Logical File (ILF)

b)  External Interface File (EIF)

c)  External Input (EI)

d)  External Output (EO)

e)  External Inquiry (EQ)

Answer: D

14.	Something that includes a combination of inputs and outputs for retrieving data from either the internal files or from files external to the application would be called an:

a)  Internal Logical File (ILF)

b)  External Interface File (EIF)

c)  External Input (EI)

d)  External Output (EO)

e)  External Inquiry (EQ)

Answer: E

15.	LOC  in a software application program

a)  can be used to illustrate the fact that experienced programmers tend to write more code than novice programmers would in coding the same project.

b)  is a superior method of measuring programmer productivity.

c)  would have a similar value for a program written in Assembler as would the same program written in Visual Basic.

d)  is easier to count once the program is written than it is to estimate how many lines of code will be actually required to write the program.

e)  takes into account the complexity, constraints, and influencers of a project.

Answer: D

Short Answer Questions

- Describe the PMBOK area of project time management.

The Project Management Body of Knowledge (PMBOK) area called project time management focuses on the processes necessary to develop the project schedule and to ensure that the project is completed on time. As defined in the PMBOK, project time management includes:

- Activity definition—identifying what activities must be completed in order to produce the project scope deliverables.

- Activity sequencing—determining whether activities can be completed sequentially or in parallel and any dependencies that may exist among them.

- Activity resource estimation – identifying the type of resources (people, technology, facilities, etc.) and the quantity of resources needed to carry out project activities.

- Activity duration estimation—estimating the time to complete each activity.

- Schedule development—based upon the availability of resources, the activities, their sequence, and time estimates, a schedule for the entire budget can be developed.

- Schedule control—ensuring that proper processes and procedures are in.

2. What is a WBS? What purpose does it serve?

A work breakdown structure (WBS) provides a hierarchical structure that outlines the activities or work that needs to be done in order to complete the project scope. The WBS also provides a bridge or link between the project’s scope and the detailed project plan that will be entered into a project management software package.

3. Discuss why a project’s scope must be tied to the WBS.

Once the project’s scope is defined, the next step is to define the activities or tasks the project team must do to fulfill the scope deliverable requirements. The work breakdown structure (WBS) is a useful tool for developing the project plan and links the project’s scope to the schedule and budget. The WBS provides a framework for developing a tactical plan to structure the project work.

4. What is a work package?

The WBS decomposes, or subdivides, the project into smaller components and more manageable units of work called work packages. Work packages provide a logical basis for defining the project activities and assigning resources to those activities so that all the project work is identified. (p. 134-135)

5. What is the difference between a deliverable and a milestone?

- Deliverables

  - –Tangible, verifiable work products

  - –Reports, presentations, prototypes, etc.

- Milestones

  - Significant events or achievements

  - Acceptance of deliverables or phase completion

6. What purpose do milestones serve?

Milestones provides evidence that that deliverable has been completed or that a phase is formally over.

7. What are some advantages of including milestones in the WBS?

If a project team succeeds in meeting all of its scheduled milestones, then the project should finish as planned. Milestones can keep the project team focused and they can motivate a project team if their attainment is viewed as a success. Milestones also reduce the risk of a project. The passing of a milestone, especially a phase milestone, should provide an opportunity to review the progress of the project.

8. What is a crux? Why should the project manager and project team identify the cruxes of a project?

A crux is a proof of concept. A crux can be the testing of an idea, concept, or technology that is critical to the project’s success. Solving a crux is a milestone that would encourage the organization to invest more time and resources to complete the project.

9. What is the proper level of detail for a WBS?

The level of detail should support not only the development of the project plan but also allow the project manager and project team to monitor and compare the project’s actual progress to the original plan’s schedule and budget. The two most common errors when developing a WBS are too little or too much detail. Too little detail may result in a project plan that overlooks and omits important activities and tasks. This will lead to an overly optimistic schedule and budget. On the other hand, the WBS should not be a to-do list of one-hour tasks. This excessive detail results in micromanagement that can have several adverse effects on the project.

10. Why should the WBS be deliverable-oriented?

The focus of a project should be to produce something, not merely on completing a specified number of activities. It may be necessary to repeat an activity or task until quality standards are met.

11. Explain why people who do the work on a project should be involved in developing the project plan?

Developing the WBS may require several versions until everyone is comfortable and confident that all of the work activities have been included. It is also a good idea to involve those who will be doing the work—after all, they probably know what has to be done better than anyone else.

12. How does the concept of knowledge management support the development of the project plan?

By using the concept of learning cycles, the project team can focus on what they know (the facts), what they think they know (assumptions), and what they need to find out (research) in order to develop a more useful WBS. Lessons learned from previous projects can be helpful in ensuring that the WBS and subsequent project plan are realistic and complete.

13. How is estimating an IT project different from estimating a construction project?

The challenge of estimating an IT project lies in trying to estimate something that is logical, rather than physical like a construction project.

14. What makes estimating an IT project challenging?

In an IT project, often specific requirements, in terms of features and functionality, are generally not defined until later, during the design phase. In addition, the complexity and technical challenges of implementing those features are either unknown or optimistically glossed over in the early stages of the project. As a result, estimating an IT project can be like trying to hit a moving target—hitting either one accurately requires continuous adjustments.

15. What is guesstimating? Why should a project manager not rely on this technique for estimating a project?

Guesstimating is picking numbers out of the air or off the top of one’s head. It should not be relied on for many reasons, but the most common error when guesstimating is to be overly optimistic and to underestimate the requirements to complete a project.

16. Describe the potential problems associated with providing an off-the-record estimate?

There is always the risk of the off-record guesstimate becoming the requirement of record. Underestimating can result in long hours, reduced quality, and unmet client expectations.

17. What is the Delphi technique? When would it be an appropriate estimating technique for an IT project?

The Delphi technique requires several experts who are recruited to estimate the same item. Based upon information supplied, each expert makes an estimate and then all the results are compared. If the estimates are reasonably close, they can be averaged and used as an estimate. Otherwise, the estimates are distributed back to the experts who discuss the differences and then make another estimate. In general, these rounds are anonymous and several rounds may take place until a consensus is reached. It can be very effective and provide reasonable assurance when the stakes are high and the margin for error is low.

18. What is time boxing? What are some advantages and disadvantages of time boxing project activities?

Time boxing is a technique whereby a box of time is allocated for a specific activity or task. This allocation is based more on a requirement rather than on just guesswork. Used effectively, time boxing can help focus the project team’s effort on an important and critical task. The schedule pressure to meet a particular deadline, however, may result in long hours and pressure to succeed. Used inappropriately or too often, the project team members become burned out and frustrated.

19. Describe top-down estimating. What are some advantages and disadvantages of top-down estimating?

Top-down estimating involves estimating the schedule and/or cost of the entire project in terms of how long it should take or how much it should cost. It may allow one to respond to a requirement from the business environment. Top-down estimating works well when the target objectives are reasonable, realistic, and achievable. Top-down estimating can be a very effective approach to cost and schedule analysis. More specifically, a top-down approach may force the project manager to examine the project’s risks more closely so that a specific budget or schedule target can be achieved. By understanding the risks, trade-offs, and sensitivities objectively, the various project stakeholders can develop a mutual understanding that leads to better estimation. When made by people independent from the project team, however, these targets are often overly optimistic or overly aggressive. These unrealistic targets often lead to what Ed Yourdon (1999) calls a death march project.

20. Describe bottom-up estimating. What are some advantages and disadvantages of bottom-up estimating?

Bottom-up estimating involves dividing the project into smaller modules and then directly estimating the time and effort in terms of person-hours, person-weeks, or person-months for each module. The project manager, or better yet the project team, can provide reasonable time estimates for each activity. Bottom-up estimated is straightforward; however, confusing effort with progress can be problematic. When doing bottom-up estimating often analogous estimating is employed. If the analogy is not well chosen or unanticipated differences emerge, the estimation error will likely be compounded.

21. What is a death march project? What situations in project planning can lead to a death march project?

The term is used as a metaphor, to suggest a “forced march” imposed upon relatively innocent victims, the outcome of which is usually a high casualty rate. Project parameters include schedule, staff, budget or other resources, and the functionality, features, performance requirements, or other aspects of the project. A death march software project means one or more of the following constraints has been imposed:

- The project schedule has been compressed to less than 50 percent of its original estimate.

- The staff originally assigned or required to complete the project has been reduced to less than 50 percent.

- The budget and resources needed have been reduced by 50 percent or more.

- The functionality, features, or other performance or technical requirements are twice what they should be under typical circumstances.

22. Discuss why adding people to a project that is already behind schedule can make it later?

When schedule slippage is recognized, the natural tendency (and traditional) response it to add more manpower. Like dousing a fire with gasoline, this makes matters worse, much worse. More fire requires more gasoline, and thus begins a regenerative cycle which ends in disaster.” Brooks Law, “Adding manpower to a late software project makes it later.” When new people are added, often the time it takes to acclimate them to the project, bring them up to speed on what has gone on before their arrival, and fit them into a productive role in the now larger project is greater than the time saved by their output.

23. What is software engineering?

The discipline of software engineering focuses on the processes, tools, and methods for developing a quality approach to developing software.

24. Why is counting lines of code (LOC) a popular method for estimating and tracking programmer productivity? What are some problems associated with this method?

Counting lines of code seems intuitively obvious—a 1,000 LOC Java program will be ten times larger than a 100 LOC Java program—counting LOC is not all that straightforward. First, what counts as LOC? Adding comments or declaring variables may or may not count a LOC. In addition, experienced programmers tend to write less code than novice programmers. After all, an experienced programmer can write more efficient code, code that does the same thing in fewer lines of code than a novice programmer would use. The same can be said for different programming languages. In fact, one could argue that counting LOC could encourage programmers to write inefficient code, especially when LOC are used as a productivity metric. Finally, it is much easier to count the lines of code after a program is written than it is to estimate how many lines of code will be required to write the program.

25. What is a function point? What advantages do function points have over counting lines of code?

Function points are a synthetic metric, similar to ones used every day, such as hours, kilos, tons, nautical miles, degrees Celsius, and so on. However, function points focus on the functionality and complexity of an application system or a particular module. Function points are independent of the technology. We can compare one application written in one language with another application developed in another. Moreover, function point analysis is reliable—i.e., two people who are skilled and experienced in function point analysis will obtain function point counts that are the same, that is, within an acceptable margin of error.

26. How can function point analysis be used to help manage scope creep?

Early on in the project, a function point analysis can be conducted based on the project’s scope. Then a more detailed analysis of the user’s requirements can be made during the analysis and design phases. Then, function point analysis can and should be conducted at various stages of the project life cycle. For example, a function point analysis conducted based on the project’s scope definition can be used for estimation and developing the project’s plan. During the analysis and design phases, function points can be used to manage and report progress and for monitoring scope creep.

27. What is backfiring? How could an organization use backfiring to improve the accuracy of estimating IT projects?

Backfiring is a technique which allows direct conversion from an application’s source code to an equivalent function point count. Backfiring can provide an easy way to create a function point inventory of an organization’s project portfolio.

28. What is COCOMO?

COCOMO is an acronym for COnstructive COst MOdel, which was first introduced in 1981 by Barry Boehm in his book Software Engineering Economics. Based on LOC estimates, it is used to estimate cost, effort, and schedule.

29. Under the COCOMO model, describe the organic, semi-detached, and embedded models.

Project types can be classified as:

- Organic—These are routine projects where the technology, processes, and people are expected to all work together smoothly. One may view these types of projects as the easy projects where few problems are expected.

- Embedded—An embedded project is viewed as a challenging project. For example, it may be a system to support a new business process or an area that is new ground for the organization. The people may be less experienced, and the processes and technology may be less mature.

- Semi-Detached—If organic projects are viewed as easy and embedded as difficult or challenging, then semi-detached fall somewhere in the middle. These projects may not be simple and straightforward, but the organization feels confident that its processes, people, and technology in place are adequate to meet the challenge.

30. What are heuristics? Discuss some of the advantages and disadvantages of using heuristics for estimating IT projects.

Heuristics are rules of thumb. Heuristic approaches rely on the fact that the same basic activities will be required for a typical software development project and these activities will require a predictable percentage of the overall effort. The main advantage of heuristics is that they are easy to use. The major disadvantage is that they are not accurate.

31. What can lead to inaccurate estimates? How can an organization improve the accuracy of estimating IT projects?

Improper application of an estimating technique or reliance on a single method of estimating can lead to inaccurate estimates. From the “Mythical Man Month” we learn: “First, our techniques of estimation are poorly developed. More seriously, they reflect an unvoiced assumption which is quite untrue—i.e., that all will go well.” “Second, our estimating techniques fallaciously confuse effort with progress, hiding the assumption that men and months are interchangeable.” “Third, because we are uncertain of our estimates, software managers often lack the courteous stubbornness of Antoine’s chef: Good cooking takes time. If you are made to wait, it is to serve you better, and to please you.” (From the menu of Antoine’s, a restaurant in New Orleans)

Estimating the effort and duration of an IT project is not an exact science. No single method or technique will provide 100 percent accuracy. Using a combination of approaches may help triangulate an estimate, which provides a confidence greater than when merely guessing or using a single estimation technique. To be realistic, estimates should be revised as understanding of the project increases and new information acquired. Accurate estimating is a function of applying a process and recognizing that effort must be expended in creating a baseline of experience that will allow for increased accuracy of that process. Estimating does not require a crystal ball; it simply requires commitment.

32. What is the impact of consistently estimating too low? Too high?

Underestimating can result in long hours, reduced quality, and unmet client expectations. The schedule pressure to meet deadlines may result in long hours and pressure to succeed. Ultimately, the project team members may become burned out and frustrated. Credibility will suffer with consistently misestimating either too high or too low. Estimating too high can lead to missed opportunities and rejection of what would have been profitable projects. If one consistently estimates too high, management may assume all estimates you produce are “fat” and automatically cut time and budget from any estimate you provide; setting you up for a death march project.

Essay Questions

1.	What are some of the advantages and disadvantages of a project team working together to develop the project plan?

2	Describe the estimation technique called Guesstimating. What are the strengths and weaknesses of this approach?

3.	Describe the estimation technique called the Delphi Technique. What are the strengths and weaknesses of this approach?

4.	Compare and contrast top-down and bottom-up estimating? Why would you choose one method over the other?

5.	What is software engineering and how does it utilize metrics.

6.	What are the pitfalls of using lines of code to measure efficiency and productivity of programmers?

7.	What are the underlying assumptions of function point analysis and how do these assumptions support project estimation.

8.	What are heuristics and what situations would likely lead one to use them? What are the risks of using heuristics for project estimation?

9.	What is the benefit of using automated estimating tools? What does research have to say about projects that use formal estimating tools?

10.	What is the best way to estimate IT projects?