Chapter 9: Project Communication, Tracking, and Reporting

True/False

- The project manager must have a clear picture of how the actual progress or work compares to the baseline plan in order to make well-informed decisions, take appropriate actions, or to make adjustments to the project plan.

  - True

  - False

True

- All of the project stakeholders should receive exactly the same information regarding the project’s progress in order to eliminate any miscommunication.

  - True

  - False

False

- The project communications plan may be informal depending on the needs of the project stakeholders and the size of the project.

  - True

  - False

True

- If a stakeholder has been judged to adversarial and having a vested interest in the failure of your project, it would probably be wise to keep him/her out of the communication loop.

  - True

  - False

False

- A project metric should be obtained from observable, quantifiable data that allows the team and other stakeholders to gauge the efficiency and effectiveness of the work being done.

  - True

  - False

True

- One attribute of a good project metric is that it should be subjective so that a stakeholder can understand the project manager’s personal opinion or insight as to how the project is progressing.

  - True

  - False

False

- A good project metric should be understandable, quantifiable, cost effective, proven, and be effective.

  - True

  - False

True

- The project champion should design a measurement system to gauge the progress of the project team because he or she has a vested interest in the project’s outcome.

  - True

  - False

False

- Generally, the more metrics one adopts, the greater the project control.

  - True

  - False

False

- The project team should design its own measurement system.

  - True

  - False

True

- The planned value (PV) tells us how much of our project will be completed in each time increment.

  - True

  - False

False

- Planned value (PV) is the planned or budgeted cost of work scheduled for an activity or component of the WBS.

  - True

  - False

True

- Earned value is often referred to as the budgeted cost at completion (BAC).

  - True

  - False

False

- Earned value provides a performance measurement that tells us how much of the budget we really should have spent for the work completed so far.

  - True

  - False

True

- Budget At Completion (BAC) is the total planned cost of a project.

  - True

  - False

True

- If EV – AC is positive, you have a positive Cost Variance and this tells us that the project is under budget.

  - True

  - False

True

- As a project manager, you would be pleased see a  Cost Performance Index CPI less than one (1) for your project

  - True

  - False

False

- The Schedule Performance Index (SPI) for our project is greater than one (1) and so we would anticipate that all other things being equal, our project will finish ahead of schedule.

  - True

  - False

True

- The schedule variance (SV) shows the difference between the current progress of the project and its original or planned value.

  - True

  - False

True

- A cost variance (CV) can be positive or negative, but never zero.

  - True

  - False

False

- The Expected Time Complete (ETC) provides an estimate for completing the scheduled work that remains.

  - True

  - False

True

- The Estimate At Completion (EAC) is a project metric that can be used to estimate the most likely total or final cost of the project based on the project’s performance and any risks that should be considered.

  - True

  - False

True

- The purpose of a project review is to not only show evidence that the project work is being completed, but also that the work is being completed according to various standards or agreed upon requirements.

  - True

  - False

True

- Given the advances that have been made in telecommunications and IT technology in general, there is little value or necessity today for Face-to-Face (F2F) meetings.

  - True

  - False

False

- Internet and Web-Based technologies have a significant role to play in communication and collaboration efforts of project teams.

  - True

  - False

True

Multiple Choice

1.	Earned Value tells us __________

a)  how much we actually spent for work completed

b)  how much we budgeted to spend at the beginning of the project

c)  how much of the budget we have left to spend on the project

d)  how much of the budget we really should have spent on the work completed so far

e)  None of the above

Answer: D

2.  If you  hired a consulting firm to develop a system which  is estimated to take four months to complete with the tasks evenly divided over the four months and you agree to pay for the project with equal monthly installments, those payments would be called:

a)  Planned Value (PV)

b)  Budget At Completion (BAC)

c)  Actual Cost (AC)

d) Earned Value (EV)

e)  None of the above

Answer: A

3	If we know the Actual Cost of a WBS component, what other value do we need to know in order to calculate the cost performance index (CPI)?

a)  Budget at Completion (BAC)

b)  Budget costs of remaining work (BCRW)

c)  Schedule Variance (SV)

d)  Expected Time Complete (ETC)

e)  Earned Value (EV)

Answer: E

4.	Cost Variance (CV) = Earned Value - ___________.

a)  Budget at Completion (BAC)

b)  Budgeted cost of remaining work (BCRW)

c)  Schedule Variance (SV)

d)  Actual Cost (AC)

e)  None of the above

Answer: D

5.	EV-AC =

a)  Cost performance index (CPI)

b)  Scheduled performance index (SPI)

c)  Cost Variance (CV)

d)  Minimum funds needed (MFN)

e)  None of the above

Answer: C

6.	Barring a change in project scope and given a Cost Performance Index (CPI)  that is less  than 1,  the most reasonable inference to draw is that:

a)  The project will likely finish earlier than planned.

b)  The project will likely finish later than planned.

c)  The project will likely cost more than planned.

d)  The project will likely cost less than planned.

e)  The project will likely be on time and on budget.

Answer: C

7.	Barring a change in project scope and given a Schedule  performance index (SPI)  that is greater than 1, the most reasonable inference to draw is that:

a)  The project will likely finish earlier than planned.

b)  The project will likely finish later than planned.

c)  The project will likely cost more than planned.

d)  The project will likely cost less than planned.

e)  The project will likely be on time and on budget.

Answer: A

8.	A _________ tells us what the project team has accomplished.

a)  Budget report

b)  Status report

c)  Progress report

d)  Forecast report

e)  News report

Answer: C

9.	Which of the following is not likely a characteristic of a good project metric?:

a)  Understandable

b)  Quantifiable

c)  Cost Effective

d)  Subjective

e)  High Impact

Answer: D

- Information distribution includes all of the following EXCEPT

  - Face-To-Face Meetings

  - Telephone, e-mail, and other wireless devices

  - Web-based technologies

  - Threaded discussion areas

  - All of the above are examples of information distribution

Answer: E

- The budgeted cost of work scheduled for an activity or component of the WBS is the

  - Planned Value (PV)

  - Budget At Completion (BAC)

  - Actual Cost (AC)

  - Expected Time Complete (ETC)

  - Estimate at Completion (EAC)

Answer: A

- The metric that provides an estimate of the most likely total or final cost of the project based on the project’s performance and any risks that should be considered is the

  - Planned Value (PV)

  - Budget At Completion (BAC)

  - Actual Cost (AC)

  - Expected Time Complete (ETC)

  - Estimate at Completion (EAC)

Answer: E

- The cost incurred for completing a scheduled task or WBS component is the

  - Planned Value (PV)

  - Budget At Completion (BAC)

  - Actual Cost (AC)

  - Expected Time Complete (ETC)

  - Estimate at Completion (EAC)

Answer: C

- The total planned cost of the project is computed before the project work begins.  This metric is called the

  - Planned Value (PV)

  - Budget At Completion (BAC)

  - Actual Cost (AC)

  - Expected Time Complete (ETC)

  - Estimate at Completion (EAC)

Answer: B

- A metric that provides an estimate for completing the scheduled work that remains once the project is started is called the

  - Planned Value (PV)

  - Budget At Completion (BAC)

  - Actual Cost (AC)

  - Expected Time Complete (ETC)

  - Estimate at Completion (EAC)

Answer: D

- The PMBOK® area called project communications management includes which of the following?

  - Communications planning

  - Information distribution

  - Performance reporting

  - Administration closure

  - All of the above are part of project communications management

Answer: E

Short Answers

1. Why should a project manager be concerned with monitoring a project’s progress?

Project sponsors do not like surprises. Regardless of how well a project is planned, unexpected situations will arise. These unexpected events will require adjustments to the project schedule and budget. In fact, many cost overruns and schedule slippages can be attributed to poorly monitored projects.

2. Describe the PMBOK® area called communications planning.

Communications Planning—Communications planning attempts to answer the following questions:

- How will information be stored?

- How will knowledge be stored?

- What information goes to whom, when, and how?

- Who can access what information?

- Who will update the information and knowledge?

- What media of communication is best?

Information Distribution—Focuses on getting the right information to the right people in the right format. Moreover, information distribution should also include organizing minutes from meetings and other project related documents.

Performance Reporting—Focuses on the collection and dissemination of project information to the various project stakeholders. This should include status reports, progress reports, and forecast reports.

Administrative Closure—Focuses on verifying and documenting the project’s progress.  This includes organizing and archiving project records and lessons learned.

3. Compare the information requirements of a project sponsor to those of a project team member. How are they similar? How are they different?

The project client or sponsor may be interested in the overall performance of the project. More specifically, is the work defined in the project scope being completed on time and within budget? And what is the likelihood of the project achieving its MOV? On the other hand, members of the project team may be interested in knowing what tasks or activities they should be working on and how their work relates to the activities and tasks being performed by other members of the project team. It is important that the people doing the actual work be empowered to take corrective action so that problems and issues can be resolved sooner rather than later.

4. What kinds of contingencies would be difficult for a project manager to anticipate when developing the project plan?

Contingencies that lie in the environment outside of the project manager’s control may be difficult to anticipate. Examples include a key project team member leaving, the client, vendor, or subcontractor going out of business, and natural disaster.

5. What is the purpose of a project communications plan? What kinds of things should this plan address?

The purpose of a project communications plan is to ensure that all of the project stakeholders know how their interests stand in relation to the project’s progress. The plan should address the following questions:

- Who has specific information needs?

- What are those information needs?

- How will a particular stakeholder’s information needs be met?

- When can a stakeholder expect to receive this information?

- How will this information be received?

6. Why is effective and efficient communication vital to a project?

It is important that everyone associated with the project know what is going on. A project manager can develop an accurate and realistic project plan, but that plan is useless unless it is executed effectively. And, because no project plan is perfect, communication allows timely and intelligent adjustments to be made so it can be executed effectively.

7. What are project metrics?

A project metric may be defined as a qualitative measurement of some attribute of the project. This metric should be obtained from observable, quantifiable data (Edberg 1997). In addition, these metrics can be useful for developing a measurement program that allows the team and other stakeholders to gauge the efficiency and effectiveness of the work being done.

8. Describe the qualities of a good project metric.

Understandable—A metric should be intuitive and easy to understand; otherwise, the metric will be of little value and will most likely not be used.

Quantifiable—A quantifiable metric is objective. A metric should have very little bias as a result of personal influence or subjectivity.

Cost Effective—Data must be collected in order to produce a metric. Subsequently, a metric should be relatively easy and inexpensive to create and should not be viewed as a major disruption.

Proven—A metric should be meaningful, accurate, and have a high degree of validity in order to be useful. The metric must measure exactly what one wants to measure. “What gets measured gets done!”

High Impact—Although the efficiency of computing a metric is important, the metric must be effective. Why measure something that has little impact on the project?

9. Why should a project have a good measurement system in place?

As Meyer (1994) suggests, trying to run a team without a good measurement system is like trying to drive a car without a dashboard. He suggests the following principles as a guide:

    - A measurement system should allow the team to gauge its progress

    - The team should design its own measurement system

    - Adopt only a handful of measures

    - Measures should track results and progress

10. Discuss why a good measuring system should guide the progress of the project team rather than management alone.

Having a good measuring system in place will let the team know when to take corrective measures without waiting for management to discover the project is off track and needs correcting. Having a few good project metrics will help keep the team focused and will create a common language among the team members and project stakeholders.

11. What are the advantages of having the project team design its own metrics and measuring system?

Among the reasons the team should design its own metrics and measuring system are the notions that the people actually doing the work tend to know what metrics are best suited and furthermore if the team is involved in developing the metrics, they will have a sense of ownership in the measures and likely be more committed to being guided by them.

12. If “what gets measured gets done,” why should a project team not be accountable to numerous project metrics?

Adding more and more measures as a means of encouraging team members to work harder can have the opposite effect. Collecting data to support a measurement system takes time and can interfere with the planned work.

13. Describe the concept of earned value.

Earned value (EV) provides a performance measurement that tells us how much of the budget for a given task, WBS component, or the project, that we really should have spent for the work completed so far.

14. What is Planned Value (PV)?

Planned Value (PV) is the planned or budgeted cost of work scheduled for an activity or component of the work breakdown structure.

15. What is Actual Cost (AC)?

Actual Cost (AC) is the total cost incurred for completing a scheduled task or work breakdown structure component.

16. What is Budget at Completion (BAC)?

The budgeted at completion (BAC) is total planned cost of a project.

17. Describe how the SPI and CPI can be used to forecast the final cost of a project.

The schedule performance index (SPI) provides a ratio of the work performed to the work scheduled. This metric provides a measure of schedule efficiency. An SPI ratio greater than one indicates that the project is ahead of schedule and an SPI under one indicates the project is behind schedule. The cost performance index (CPI) tells us how much work we are completing for every dollar we spend. It is the ratio the budgeted cost of work performed to the actual cost of work performed. Suppose one were to calculate the SPI and the CPI in the midst of a project and find their values different from one (i.e. the project is ahead or behind schedule and over or under budget). If nothing changes (i.e., the project’s performance does not get any better or any worse) then the minimum cost of completing the project could be estimated by dividing the original total budget by the CPI. However, if the SPI ratio were to persist and things continued to get better or worse (depending on the SPI value), then the final project cost could be estimated by dividing the original budget by the product of the CPI and the SPI.

18. What is a project review and what purpose does it serve?

Project reviews may be formal or informal meetings that include various project stakeholders.  These reviews may focus on specific deliverables, milestones, or phases. The purpose of a review is to not only show evidence that the project work has been completed, but also that the work has been completed according to certain standards or agreed upon requirements.

19. What is a status report?

A status report describes the present state of the project. In general, a status report compares the project’s actual progress to the baseline plan. Analogous to a balance sheet used by accountants, a status report may include, for example, a variance analysis that compares actual schedule and cost information to the baseline schedule and budget.

20. What is a progress report?

A progress report tells us what the project team has accomplished. This report may compare the activities or tasks that were completed to the activities or tasks outlined in the original project network.

21. What is a forecast report?

A forecast report focuses on predicting the future status or progress of the project. For example, it may include a trend analysis that tells us when the project is most likely to finish and how much it will cost.

22. When are face-to-face meetings more appropriate than phone calls or email?

The advantage of face-to-face meetings is that one can see other people’s expressions and body language. Sometimes the way someone says something can be more expressive than what they say.

23.  Describe the role IT can play in supporting the project communications plan.

Cellular phones, pagers, and other wireless devices are commonplace and have increased our mobility and accessibility. Although these communication devices are not as personal as face-to-face meetings, they certainly make communication possible when people cannot be at the same place at the same time.

24. When are Internet, intranet, and extranet applications appropriate in supporting the project communications plan?

For example, an Internet application would be available to anyone who has access to the World Wide Web or Internet. An intranet, on the other hand, may be developed using the same technology, but access is limited to the project team by means of passwords or firewalls. An extranet may include others outside the immediate project team or organization, such as the project sponsor or client. Similar to an intranet, access may be limited through the use of passwords or firewalls.

- Give an example of a type of meeting project stakeholders may have under the following circumstances.  Describe how IT might support their communications needs.

      - Same time – same place Users and developer meeting face to face to develop a prototype

      - Same time – different places Users and developers meeting via teleconference to discuss requirements.

      - Different times – same place – An intranet application could be used so users and developers could list problems and fixes during testing

      - Different times – different places – Email to send status reports.

Essay Questions

1.	Briefly describe the four aspects of communication that are included in the PMBOK® area called project communications management.

2	Why is communications among project stakeholders so important?

3.	Why would a project manager be unwilling to share bad news about unexpected problems with senior management or other high profile stakeholders?

4.	Sketch out a table with headings that represent the essential elements of a project communications plan. Fill in a hypothetical entry under each heading.

5.	What are the characteristics of a good project metric?

6.	Explain the concept of Earned Value and illustrate it with hypothetical values.

7.	How is the Cost Performance Index calculated and what can one learn from computing it?

8.	How is the Schedule Performance Index calculated and what can one learn from computing it?

9.	Briefly describe the common categories of project reporting.

10.	What are the strengths and weaknesses of the major information distribution channels covered in the text?