Chapter 5: Defining and Managing Project Scope

True/False

- According to the PMBOK® area of scope management, one of the processes is scope planning which means ensuring that authority and resources are committed to developing a scope management plan.

  - True

  - False

False

- Scope definition defines the project boundary.

  - True

  - False

False

- Scope verification confirms that the scope is complete and accurate.

  - True

  - False

True

- Scope change control procedures protect the scope boundary from expanding as a result of increasing featurism.

  - True

  - False

True

- Since adding features to a project will likely have a negative impact on schedules and budgets, once the project’s scope has been defined, no new features should added.

  - True

  - False

False

- The scope statement documents the sponsor’s needs and expectations.

  - True

  - False

True

- The scope boundary establishes only those elements that are a part of the project work to be completed by the project team.

  - True

  - False

False

- The scope boundary establishes both what is, and what is not part of the project work to be completed by the project team.

  - True

  - False

True

- Project scope is a statement detailing the features and functions that must support the IT solution.

  - True

  - False

False

- Project scope defines the work boundaries and deliverables of the project.

  - True

  - False

True

- One way to communicate the project’s deliverables is to create a deliverable definition table.

  - True

  - False

True

- The development of a deliverable structure chart is an interim step to define detailed work packages used to estimate the project schedule and budget.

  - True

  - False

True

- The development of a work breakdown structure is an interim step to define detailed work packages used to estimate the project schedule and budget.

  - True

  - False

False

- Product scope is a statement detailing the deliverables and activities that support the IT methodology.

  - True

  - False

False

- Actors are people or external systems that are elements of a data flow diagram (DFD).

  - True

  - False

False

- The use case diagram, a feature of the UML, is useful for defining the product scope.

  - True

  - False

True

- Scope grope suggests a fundamental and significant change in the project scope.

  - True

  - False

False

- Joint application development is a group-based method where end users define the system requirements or design the system.

  - True

  - False

False

- Joint application development is a group-based method where users and systems analysts jointly define the system requirements or design the system.

  - True

  - False

True

- Scope change control is concerned with ensuring that any changes to the project scope will be beneficial, with determining that an actual scope change has occurred, and with managing the actual changes when and as they occur.

  - True

  - False

True

Multiple Choice

1.  Which of the following components or processes of a scope management plan most directly deals with the problem illustrated by a project team spent a great amount of time on a set of activities that did not support the project MOV.

a)  Scope Planning

b)  Scope Definition

c)  Scope Boundary

d)  Scope Initiation

e)  Scope Verification

Answer: C

2.  Which PMBOK® defined process within the knowledge area of project scope management confirms the project's scope is complete and accurate?

a)  Project scope initiation

b)  Scope planning

c)  Scope definition

d)  Scope verification

e)  Scope change control

Answer: D

3.  Which PMBOK® defined process within the knowledge area of project scope management gives the project manager the authority to develop a scope management plan?

a)  Project scope initiation

b)  Scope planning

c)  Scope definition

d)  Scope verification

e)  Scope change control

Answer: B

4.  Which PMBOK® defined process within the knowledge area of project scope management is responsible for defining what work will and will not be part of the project?

a)  Project scope initiation

b)  Scope planning

c)  Scope definition

d)  Scope verification

e)  Scope change control

Answer: C

5. Which PMBOK® defined process within the knowledge area of project scope management ensures that controls are in place to manage proposed scope changes once the project’s scope is set.

a)  Project scope initiation

b)  Scope planning

c)  Scope definition

d)  Scope verification

e)  Scope change control

Answer: E

6. Which PMBOK® defined process within the knowledge area of project scope management focuses on the decomposition or diving the major project deliverables into smaller and more manageable components?

a)  Project scope initiation

b)  Scope planning

c)  Creat work breakdown structure

d)  Scope verification

e)  Scope change control

Answer: C

7.  The concept of actors is an integral part of:

a)  Data flow diagram

b)  Use case diagram

c)  Joint application development session

d)  Deliverable structure chart

e)  Deliverable definition table

Answer: B

8.	The term scope creep is best described as:

a)  a project team's inability to define the project's scope

b)  a fundamental change in project scope

c)  the project slowdown caused by changes in the project MOV

d)  increasing featurism

e)  a scary mouthwash salesman

Answer: D

9.  Which of the following is a product-oriented scope definition tool?

a)  context level data flow diagram

b)  deliverable structure chart

c)  deliverable definition table

d)  work breakdown structure

e)  none of the above

Answer: A

Short Answer Questions

1. What is meant by project scope?

The term scope is used to define the work boundaries and deliverables of the project so what needs to get done, gets done—and only what needs to get done, gets done.

2. Briefly describe the five scope management processes.

- scope planning: The development of a scope management plan that defines the project’s scope and how it will be verified and controlled throughout the project.

- Scope definition: A detailed scope statement that defines what work will and will not be part of the project and will serve as a basis for all future project decisions.

- Create work breakdown structure: The decomposition or dividing of the major project deliverables into smaller and more manageable components.

- scope verification: Confirmation and formal acceptance that the project’s scope is accurate, complete, and supports the project’s MOV.

- scope change control: Ensures that controls are in place to managed proposed scope changes once the project’s scope is set.  These procedures must be communicated and understood by all project stakeholders.

3. Briefly describe the scope planning process.

Scope planning is a process for defining and documenting the project work. More specifically, a project’s scope defines all the work, activities, and deliverables that the project team must provide in order for the project to achieve its MOV. It is an important step in developing the project plan since one must know what work must be done before an estimate can be made on how long it will take and how much it will cost.

4. Briefly describe the scope definition process.

Developing a scope statement is a useful first step for defining the scope of the project and setting a boundary. A project’s scope, however, should also be defined in terms of the deliverables that the team must provide. These deliverables can be divided into project-oriented deliverables and product-oriented deliverables. This separation gives the team a clearer definition of the work to be accomplished and improves the likelihood of accurately assigning resources and estimating the time and cost of completing the work. Moreover, a clear definition of the project’s deliverables sets unambiguous expectations and agreement among all of the project stakeholders.

5. Briefly describe the scope verification process.

Project scope verification is the scope management process that provides a mechanism for ensuring that the project deliverables are completed according to the standards described in the DDT. Gray and Larson (2000) provide a project scope checklist for ensuring that the deliverables are completed—and completed correctly. The checklist items include: MOV, Deliverables, Quality standards, Milestones, Review and acceptance.

6. Briefly describe the scope change control process.

Scope change control is concerned with ensuring that any changes to the project scope will be beneficial, with determining that an actual scope change has occurred, and with managing the actual changes when and as they occur. Scope control is also concerned with: Scope grope, Scope creep, and Scope leap.

7. Describe the scope management plan.

Together, the processes and techniques for defining and managing scope make up the scope management plan. Depending on the size and nature of the project, this plan can be separate and/or summarized in the project charter. Regardless, Figure 5.1 summarizes the components and processes of a scope management plan. The outer ring is comprised of the scope management processes and the inner ring is comprised of the deliverables and components that support the processes and which when combined with the processes define the illustration center, the scope.

8. Why is it important to define the project’s scope accurately and completely?

The procedures for defining and managing the scope of a project must be communicated and understood by all of the project’s stakeholders to minimize the likelihood of misunderstandings. Moreover, the project’s scope must align and support the project’s MOV. Why spend time and resources to perform work that will not add any value to the organization or help the project achieve its MOV? Again, work that does not add value consumes valuable time and resources needlessly.

9. What is a scope boundary?  What purpose does it serve?

Defining the scope boundary is the first step to establishing what is, and what is not, part of the project work to be completed by the project team. Think of the scope boundary as a fence designed to keep certain things in and other things out. The scope boundary must protect the scope from activities that will not help the project achieve its MOV.

10. What is the difference between product-oriented deliverables and project-oriented deliverables?

Product scope therefore focuses on identifying the features and functionality of the information system to be implemented.

The role of project-oriented deliverables is to ensure that the project processes are being competed so that the project’s product (i.e., the information system) achieves the project’s MOV and objectives. Project-oriented deliverables also provide tangible evidence of the project’s progress (or lack of progress). Finally, they allow the project manager to set a baseline for performance and quality control because they usually require some form of approval before work on the next project phase or deliverable begins.

11. How does a project’s scope support the MOV concept?

The project’s scope defines and limits the project’s activities to only those things which support the project MOV. It makes sure that time and resources are only expended on things that contribute to the project MOV.

12. What is a scope statement?  What purpose does it serve?

A scope statement documents the project sponsor’s needs and expectations. It serves to clarify what work is within the scope boundary as well as what work is outside of the scope boundary and therefore not to be included.

13. What is a context dataflow diagram (DFD)?  What purpose does it serve?

A context level data flow diagram (DFD) presents a high-level representation of the system that has one process (i.e., a circle or rounded rectangle that represents the system as a whole) and depicts all the inflows and outflows of data and information between the system and its external entities. It is a useful modeling tool for refining the scope boundary and defining what the system must do.

14. How does a use case diagram help to define the project’s scope?

The use case diagram provides a simple yet effective overview of the functions and interactions between the use cases and the actors. The box separating the use cases from the actors also provides a system boundary that defines the scope boundary. Use cases inside the boundary are considered within the scope of the project, while anything outside of the boundary is considered outside the scope of the project.

15. What is a deliverable definition table (DDT)?  What purpose does it serve?

All of the project deliverables must have a clear and concise definition. One way to communicate the project’s deliverables is to create a deliverable definition table (DDT). The purpose of the DDT is to:

- define all of the project-oriented deliverables

- define the structure of the deliverable.

- define the standards that provide a means to verify whether the deliverable was produced correctly

- name the person or position responsible for approving deliverables

- list the resources required for each deliverable

16. What is a deliverable structure chart (DSC)?  How does it map to a deliverable definition table (DDT)?

Once the deliverables have been defined in the DDT, a deliverable structure chart (DSC) can be developed as an interim step to define detailed work packages that will be used to estimate the project schedule and budget. A Deliverable Structure Chart maps the project life cycle and systems development life cycle phases to the deliverables defined in the DDT.

17. What is a work breakdown structure (WBS)?  How does it map to the DDT and DSC?

A work breakdown structure (WBS) is a tool used to help create the project plan. The WBS uses the output of the DDT and DSC to develop the project plan needed to fulfill the requirements defined in the project scope.

18. Briefly describe what must be included in a scope verification checklist?

The scope verification checklist addresses:

- MOV—Are the project’s MOV clearly defined and agreed upon?

- Deliverables—Are the deliverables tangible and verifiable?

- Quality standards—Are controls in place to ensure that the work was not only completed, but also completed to meet specific standards?

- Milestones—Are milestones defined for each deliverable? Milestones are significant events that mark the acceptance of a deliverable and give the project manager and team the approval to begin working on the next deliverable.

- Review and acceptance—Are both sides clear in their expectations? The project’s scope must be reviewed and accepted by the project stakeholders.

19. What is the purpose of verifying a project’s scope?

The project scope must be verified to ensure that the deliverables are completed—and completed correctly.

20. What is the purpose of scope change control procedures?

The purpose of scope change control procedures is to ensure that any changes to the project scope will be beneficial, to determine that an actual scope change has occurred, and to manage the actual changes when and as they occur.

21. Briefly describe scope grope.

Scope grope is a metaphor that describes a project team’s inability to define the project’s scope. This situation is common early in a project when the project team and sponsor have trouble understanding what the project is supposed to accomplish.

22. Briefly describe scope creep.

Scope creep refers to increasing featurism, adding small yet time- and resource-consuming features to the system once the scope of the project has been approved.

23. Briefly describe scope leap.

Scope leap is a fundamental and significant change in the project scope.

24. What are the benefits of having scope control procedures?

The most important benefit of scope change control procedures is that they keep the project manager in control of the project. More specifically, they allow the project manager to manage and control the project’s schedule and budget. Scope control procedures also allow the project team to stay focused and on track in terms of meeting its milestones because it does not have to perform unnecessary work.

25. Briefly describe what should be included on a scope change request form.

- First, the description of the change request should be clearly defined so that the project manager and project team understand fully the nature and reason for the scope change.

- Second, the scope change should be justified, which separates the would likes from the must haves.

- Third several alternatives may be listed.

- Fourth an assessment of the impact on scope, schedule, resources, and cost.

- Fifth an approval of those scope changes to be implemented.

26. What is the purpose of a scope change request log?

To prevent requests from falling through the cracks, leading to credibility concerns and accusations that the project manager or project team is not being responsive to the client’s needs.

Essay

1.	Identify and briefly describe, the five processes that support project scope management.

2	Why is important to ensure that the project’s scope has been defined completely and accurately?

3.	What is the relationship between the project’s MOV and the project’s scope?

4.	What is increasing featurism and what are the impacts it has on a project?

5.	What is the purpose of a scope statement? Give an example of a scope statement that might address the needs of an organization which is looking to establish their first Internet web site.

6.	What is project-oriented scope and what are some of the commonly used tools to support it?

7.	Describe product-oriented scope and the tools that are available to support it.

8.	What is project scope verification and why is it an important part of project scope?

9.	The text describes three project problems with metaphorical names that scope change control is concerned with. Name and describe these problems and then illustrate how scope change control can ameliorate or remedy the problem.

10.	In developing a scope change control form, what elements should be included and why?