Chapter 8: Managing Project Risk

True/False

- Failure to follow a formal risk management plan will often cause organizations to be reactive and find themselves in a state of perpetual crisis, a condition known as crisis management.

  - True

  - False

True

- The best time to plan for risk is during the project execution phase when risk can be assessed most accurately.

  - True

  - False

False

- Effective project risk management requires that each risk have an owner.

  - True

  - False

True

- In general, because of the similarities in IT projects, one can manage all projects and risks in the same manner.

  - True

  - False

False

- Project risk management focuses solely on the downside of risk that results from unexpected problems or threats.

  - True

  - False

False

- The PMBOK® definition of project risk suggests that a systematic process is needed to effectively manage the risk of a project.

  - True

  - False

True

- It never pays to ignore an element of project risk.

  - True

  - False

False

- The goal of a sound risk management is to completely avoid all risk.

  - True

  - False

False

- Triggers or flags in the form of metrics should be identified to draw attention to a particular risk when it occurs.

  - True

  - False

True

- Unknown-unknown risks are residual risks that we cannot even imagine happening.

  - True

  - False

True

- Since risk arises from uncertainty, there can be no such category as known risks.

  - True

  - False

False

- Learning cycles can be used as a tool for identifying threats and opportunities.

  - True

  - False

True

- Nominal Group Technique is a free form, unstructured process similar to Brainstorming.

  - True

  - False

False

- The fishbone or Ishikawa diagram is a form of cause and effect analysis diagramming.

  - True

  - False

True

- Since IT projects are developed in an environment that changes so rapidly and so extensively, there is little value in using past projects to guide our risk assessment of new ones.

  - True

  - False

False

- Qualitative risk analysis has as one of its strengths the ability to include subjective analysis based on experience and judgment.

  - True

  - False

True

- The concept of expected value rests on the notion of a probability-weighted summation of component parts.

  - True

  - False

True

- Discrete Probability Distributions use only integers where fractions would make no sense.

  - True

  - False

True

- In Tusler’s risk classification scheme, Alligators are risks with a high probability of occurrence and impact.

  - True

  - False

False

- The area under the normal distribution curve that lies within 2 standard deviations of the mean (plus or minus) includes about 68% of all the values.

  - True

  - False

False

- Sensitivity analysis is used to determine the joint effects of multiple risky tasks, while Monte Carlo Simulation is used to measure which individual tasks pose the greatest project risk.

  - True

  - False

False

- The deployment of a specific risk management strategy is in part a function of risk tolerance levels of the stakeholders.

  - True

  - False

True

- Risk audits, reviews, status meetings, and reports are tools for risk monitoring and control.

  - True

  - False

True

Multiple Choice

1.	The IT Project Risk Management Processes include all of the following except:

a)  Risk Planning

b)  Risk Identification

c)  Risk Assessment

d)  Qualitative Impact Analysis

e)  Risk Evaluation

Answer: D

2.	Identifying what you know, what you think you know, and things you need to find out would be activities most closely associated with:

a)  Learning Cycles

b)  Brainstorming

c)  Nominal Group Technique

d)  Delphi Technique

e)  Cause-and-Effect Diagrams

Answer: A

3.	Gaining consensus from a group of experts would be most closely associated with:

a)  Learning Cycles

b)  Brainstorming

c)  Nominal Group Technique

d)  Delphi Technique

e)  Cause-and-Effect Diagrams

Answer: D

4.	Initial generation of ideas without evaluation would be most closely associated with:

a)  Learning Cycles

b)  Brainstorming

c)  Nominal Group Technique

d)  Delphi Technique

e)  Cause-and-Effect Diagrams

Answer: B

5.	A structured technique for identifying risks which requires participants to rank and prioritize  ideas in round-robin fashion is most closely associated with:

a)  Learning Cycles

b)  Brainstorming

c)  Nominal Group Technique

d)  Delphi Technique

e)  Cause-and-Effect Diagrams

Answer: C

6.	In which step of the risk planning process does the text say one might decide to transfer project risk to someone else (i.e.,use insurance)?

a)  risk planning

b)  risk identification

c)  risk assessment

d)  risk strategies

e)  risk monitoring and control

Answer: A

7.	Receiving a much larger than usual gas utility bill because of an early spring cold spell is an example of what type of risk?

a)  known risk

b)  known-unknown risk

c)  unknown-unknown risk

d)  known-known

e)  none of the above

Answer: B

8.	Which of the following does not represent a quadrant in Tusler's Risk Classification Scheme?

a)  Kittens

b)  Puppies

c)  Tigers

d)  Alligators

e)  Lions

Answer: E

9.	Tusler would classify  risks that have a high probability of occuring but a low impact on the project as:

a)  Kittens

b)  Puppies

c)  Tigers

d)  Alligators

e)  Lions

Answer: B

10.	Which of the following distributions has mean which is equal to (a + 4b +c) / 6 where a, b, and c are denote optimistic, most likely, and pessimistic estimates respectively?:

a)  Discrete Distribution

b)  Normal Distribution

c)  Pert Distribution

d)  Triangular Distribution

e)  Binomial Distribution

Answer: C

11.	Which of the following distributions has mean which is equal to (a +b +c) / 3  where a, b, and c are denote optimistic, most likely, and pessimistic estimates respectively?:

a)  Discrete Distribution

b)  Normal Distribution

c)  Pert Distribution

d)  Triangular Distribution

e)  Binomial Distribution

Answer: D

12.	In a normal distribution we would expect to find _______ of all values with in + or - 1 standard deviation.

a)  13%

b)  34%

c)  68%

d)  95%

e)  99%

Answer: C

Short Answer Questions

- What leads to uncertainty in an IT project?

Uncertainty comes from having to make predictions about some future events or states based on estimates, assumptions, and limited information.

- How does a project risk management approach provide an early warning signal for impending problems or issues?

The second step in the project risk management planning process is risk identification. If this step is carefully addressed, potential problem areas will likely be highlighted early.

- What is meant by crisis management? And why do many organizations find themselves in this mode?

Because of their failure to plan for the unexpected, many organizations find themselves in a state of perpetual crisis characterized by an inability to make effective and timely decisions. Many people call this approach crisis management or fire fighting because the project stakeholders take a reactive approach or only address the project risks after they have become problems.

- Describe some of the common mistakes in project risk management.

Common mistakes in managing project risk include:

- Not Understanding the Benefits of Risk Management

- Not Providing Adequate Time for Risk Management

- Not Identifying and Assessing Risk Using a Standardized Approach

- Briefly describe what is required for effective and successful project risk management.

- Commitment by all stakeholders

- Stakeholder Responsibility

- Different Risks for Different Types of Projects

- What is project risk?

PMBOK® defines project risk as: An uncertain event or condition that, if it occurs, has a positive or negative effect on the project objectives.

- What is project risk management?

PMBOK® defines project risk management as: The systematic process of identifying, analyzing, and responding to project risk. It includes maximizing the probability and consequences of positive events and minimizing the probability and consequences of adverse events.

- What are the seven IT project risk management processes?

- Risk Planning

- Risk Identification

- Risk Assessment

- Risk Strategies

- Risk Monitoring and Control

- Risk Response

- Risk Evaluation

- What types of commitment are necessary for risk planning?

Risk Planning Risk planning requires a firm commitment to the entire risk management approach from all project stakeholders. This includes a commitment to: providing resources (time, people, and technology) and undertaking the process of identifying, analyzing, and responding to threats and opportunities.

- Why can identifying IT project risks be difficult?

Risk identification can be difficult because many risks can affect a project in different ways and during different phases of the project life cycle. At times it is not possible to distinguish between internal and external risks. Finally, when attempting to address the future, there exists a category of risks (unknown-unknown) that by definition are unknowable a priori.

- What is a “known” risk? Give an example of one.

Known risks are events that are going to occur. In short, these events are like death and taxes—they will happen and there is no uncertainty about it.

- What is a “known-unknown” risk? Give an example of one.

Known-unknown risk is identifiable uncertainty. For example, if you own a home or rent an apartment, you know that you will receive a bill next month for the utilities you use. The precise amount you will owe the utility company will be unknown until you receive the actual bill.

- What is an “unknown-unknown” risk? Give an example of one.

Unknown-unknown risks are residual risks or events that we cannot even imagine happening. For example, it was not too long ago that people had never even heard about the Internet. How could they comprehend the impact it would have on many of us? Unknown-unknown risks are really just a way to remind us that there may be a few risks remaining even after we may think we identified them all. In general, these are the risks that we identify after they have occurred.

- What is the difference between an internal and external risk? Give an example of each.

Internal risks are those risks that the project manager is directly responsible for, which are direct part of the project and therefore under his/her control. It may be something like the skill set of a team member or adequacy of a project plan. External risks are risks that arise from the environment outside of the project and which are not under the project manager’s control. An earthquake that takes out a major supplier and thus puts market supply price pressure on some project inputs would be an example of an external risk. At times the distinction is not so clear as in the case where a project manager chooses an unreliable supplier because of an inadequate investigation of the qualifications of the supplier. In this case, the risk is really a result of internal processes.

- Describe some of the tools and techniques that can be used to identify IT project risks.

- Learning Cycles--identify facts (what they know), assumptions (what they think they know), and research (things to find out), to identify various risks.

- Brainstorming-- encouraging contributions from everyone in the group. Thus, initially ideas must be generated without being evaluated. Once ideas are generated by the group as a whole, they can be discussed and evaluated by the group.

- Nominal Group Technique (NGT)—

      - Each individual silently writes her or his ideas on a piece of paper.

      - Each idea is then written on a board or flip chart one at a time in a

      - The group then discusses and clarifies each of the ideas.

      - Each individual then silently ranks and prioritizes the ideas.

      - The group then discusses the rankings and priorities of the ideas.

      - Each individual ranks and prioritizes the ideas again.

      - The rankings and prioritizations are then summarized for the group.

- Delphi Technique-- a group of experts are asked to identify potential risks or discuss the impact of a particular risk. Initially, in order to reduce the potential for bias, the experts are not known to each other. Their responses are collected and made available anonymously to each other. The experts are then asked to provide another response based upon the previous round of responses. The process continues until a consensus exists.

- Interviewing--technique for identifying and understanding the nature of IT project risks is to interview various project stakeholders. This technique can prove useful for determining alternative points of view; but the quality of the information derived depends heavily on the skills of the interviewer and the interviewees, as well as the interview process itself.

- Checklists--provides a structured tool for identifying risks that have occurred in the past. They allow the current project team to learn from past mistakes or to identify risks that are known to a particular organization or industry.

- SWOT Analysis-- Strengths, Weaknesses, Opportunities, and Threats.

- Cause and Effect Diagrams— diagram can also be used for understanding the causes or factors of a particular risk.

- Past Projects-- Lessons learned from past projects can provide insight and best practices for identifying and understanding the nature of IT project risks.

- Describe the nominal group technique and how it can be applied to identifying IT project risks.

  - Each individual silently writes her or his ideas on a piece of paper.

  - Each idea is then written on a board or flip chart one at a time in a

  - The group then discusses and clarifies each of the ideas.

  - Each individual then silently ranks and prioritizes the ideas.

  - The group then discusses the rankings and priorities of the ideas.

  - Each individual ranks and prioritizes the ideas again.

  - The rankings and prioritizations are then summarized for the group.

- Describe how learning cycles can be used to identify IT project risks.

The project team and stakeholders can use this technique, whereby they identify facts (what they know), assumptions (what they think they know), and research (things to find out), to identify various risks. Using these three categories, the group can create an action plan to test assumptions and conduct research about various risks. Based on the team’s findings, both risks and lessons learned can then be documented.

- What is the Delphi Technique? How can this technique be used to identify IT project risks?

A group of experts are asked to identify potential risks or discuss the impact of a particular risk. Initially, in order to reduce the potential for bias, the experts are not known to each other. Their responses are collected and made available anonymously to each other. The experts are then asked to provide another response based upon the previous round of responses. The process continues until a consensus exists. The advantage of using the Delphi technique is the potential for getting an insightful view into a threat or opportunity; but the process takes time and may consume a good portion of the project’s resources.

- How can interviewing be used as a technique for identifying IT project risks? What are some of the advantages and disadvantages of using this technique?

A technique for identifying and understanding the nature of IT project risks is to interview various project stakeholders. This technique can prove useful for determining alternative points of view; but the quality of the information derived depends heavily on the skills of the interviewer and the interviewees, as well as the interview process itself.

- How do checklists help in identifying IT project risk? Discuss the pros and cons of using this technique.

Checklist provides a structured tool for identifying risks that have occurred in the past. They allow the current project team to learn from past mistakes or to identify risks that are known to a particular organization or industry. One problem with checklists is that they can lead to a false sense of security—i.e., if we check off each of the risks on the list, then we will have covered everything. Table 8.2 provides an example of items that may be included in a project risk checklist.

- What is SWOT analysis? How can this technique be used to identify IT project risks?

SWOT stands for Strengths, Weaknesses, Opportunities, and Threats. Brainstorming, NGT, or the Delphi technique could be used to identify and understand the nature of IT project risks by categorizing risks using the four-part framework. The usefulness of using SWOT analysis is that it allows the project team to identify threats and opportunities as well as their nature in terms of project or organizational strengths and weaknesses.

- What is a fishbone (Ishikawa) diagram? How can this tool be used to identify IT project risks?

The fishbone, or Ishikawa, diagram developed by Kaoru Ishikawa was developed to analyze the causes of poor quality in manufacturing systems. The diagram can also be used for understanding the causes or factors of a particular risk, as well as its effects. An example of an Ishikawa diagram is illustrated in Figure 8.4. The diagram shows the possible causes and effects of a key member of the team leaving the project. This technique itself can be used individually or in groups by using the following steps:

a. Identify the risk in terms of a threat or opportunity.

b. Identify the main factors that can cause the risk to occur.

c. Identify detailed factors for each of the main factors.

d. Continue refining the diagram until satisfied that the diagram is complete.

- What is the purpose of risk analysis and assessment?

Risk analysis and assessment provides a systematic approach for evaluating the risks that the project stakeholders identify. The purpose of risk analysis is to determine each identified risk’s probability and impact on the project. Risk assessment, on the other hand, focuses on prioritizing risks so that an effective risk strategy can be formulated. (p. 190)

- What is the difference between qualitative and quantitative risk analysis?

The qualitative approach includes subjective assessments based on experience or intuition. Quantitative analysis, on the other hand, is based on mathematical and statistical techniques.

- Describe the concept of expected value.

Expected value is an average, or mean, that takes into account both the probability and impact of various events or outcomes.

- What is the purpose of a decision tree? What are the advantages and disadvantages of using a decision tree?

A decision tree provides a visual, or graphical, view of various decisions and outcomes. The advantages of using a decision tree include the ability to make better decisions because they are informed by not only the magnitude of possible outcomes, but also the probability of their occurrence. Having to make decisions in a stochastic world requires allowing for uncertainty of outcomes. The deployment of a decision tree does not guarantee a successful result, because not only are the probability assessments and outcome values subjective, but even when the properly applied, low probability, undesirable outcomes still can occur.

- What is the purpose of a risk impact table?

The purpose of a risk impact table is to analyze and prioritize various IT project risks. It provides a mechanism for determining which risks should be monitored and which risks may require a response.

- What is the difference between a discrete probability distribution and a continuous probability distribution?

Discrete probability distributions use only integer or whole numbers where fractional values are not allowed or do not make sense. Continuous probability distributions are useful for developing risk analysis models when an event has an infinite number of possible values within a stated range.

- What are the rules of thumb that can be applied to a normal distribution?

- About 68 percent of all the values will fall between +1 of the mean

- About 95 percent of all the values will fall between +2 of the mean

- About 99 percent of all the values will fall between +3 of the mean

- Compare and contrast the normal distribution, the PERT distribution, and the triangular distribution.

The normal distribution is a continuous distribution and its shape is determined by its mean (µ) and standard deviation (). When graphed forms the familiar bell-shaped curve. The PERT distribution is also a continuous distribution that looks like a skewed normal distribution and is described by a three point estimate where a denotes an optimistic estimate, b denotes a most likely estimate, and c, a pessimistic estimate. The mean and standard deviation of the PERT distribution are computed as follows:

PERT Mean = (a + 4m + b) / 6

PERT Standard Deviation = (b - a) / 6

The triangular distribution is based on the same three point estimates as the PERT distribution, but with different weighting.

TRIANG Mean = (a + m + b) / 3

TRAING Standard Deviation = [((b-a)2 + (m-a)(m-b)) /18]1/2

- What is a simulation? What value do simulations provide when analyzing and assessing IT project risks?

In general, when people want to study a particular phenomenon, they pick a random sample. If you wanted to study projects, you might randomly select a certain number of projects and then collect data about certain attributes in order to make comparisons. This same approach can be used to analyze and understand how different input variables (e.g., task durations) can impact some output variable (e.g., project completion date).

- What is a Monte Carlo simulation? Describe a situation (other than the one used in this chapter) that could make good use of a Monte Carlo simulation.

Monte Carlo simulation is a technique that randomly generates specific values for a variable with a specific probability distribution. The simulation goes through a specific number of iterations or trials and records the outcome. We can perform simulations using almost any continuous or discrete probability distribution. If one was attempting to develop a budget in the face of uncertain factor input prices, a Monte Carlo simulation could be conducted that would make random picks from probability distributions that reflect ones estimation of the true underlying population parameters. One then might run a thousand simulated picks generating one thousand budget estimates which could then be averaged to calculate the expected budget costs.

- Define and discuss the four risk strategies described in this chapter.

- Accept or Ignore—Choosing to accept or ignore a particular risk is a more passive approach to risk response. The project stakeholders can either be hopeful that the risk will not occur or just not worry about it unless it does. This can make sense for risks that have a low probability of occurring or a low impact. However, reserves and contingency plans can be active approaches for risks that may have a low probability of occurring but with a high impact.

- Avoidance—The avoidance strategy focuses on taking steps to avoid the risk altogether. In this case, an active approach is made to eliminate or prevent the possibility of the threat occurring.

- Mitigate—The term mitigate means to lessen. Therefore, a mitigation risk strategy focuses on lessening the probability and/or the impact of threat if it does occur.

- Transfer—A transfer strategy focuses on transferring ownership of the risk to someone else. This transfer could be in the form of purchasing insurance against a particular risk or subcontracting a portion of the project work to someone who may have more knowledge or expertise in the particular area. As a result, this strategy may result in a premium, or added cost, to managing and responding to the risk.

- What is the difference between a management reserve and a contingency reserve?

- Management Reserves—These are reserves that are controlled and released by senior management at its discretion. These reserves are not usually included in the project’s budget, but provide a cushion for dealing with the unexpected.

- Contingency Reserves—A contingency reserve is usually controlled and released within specific guidelines by the project manager when a particular risk occurs. This reserve is usually included in the project’s budget.

- What is a contingency plan?

Contingency plans—Sometimes called an alternative plan, or Plan B, this plan can be initiated in the event a particular risk occurs. Although these types of plans are viewed as plans of last resort, they can be useful in a variety of ways.

- Why can’t a project team respond to all project risks?

A project team may be too close to the project to see the risk or opportunity and therefore fail to respond. The team may not respond to a risk because the required resources are not adequate or because the cost associated with the risk or the probability of occurrence do not warrant response.

- What is a risk response plan? What should be included?

Once the project risks and strategies are identified, they can be documented as part of the risk response plan. This plan should include the following:

- The project risk

- The trigger which flags that the risk has occurred

- The owner of the risk (i.e., the person or group responsible for monitoring the risk and ensuring that the appropriate risk response is carried out)

- The risk response based on one of the four basic risk strategies

- What are risk triggers or flags?

The risk triggers defined in the risk response plan provide risk metrics for determining whether a particular threat or opportunity has occurred.

- Why is having a risk owner a good idea? What role does a risk owner play?

The owner is someone who will be involved in the project, who will take the responsibility to monitor the project in order to identify any new or increasing risks, and who will make regular reports to the project sponsor or client. The position may also require the risk owner to ensure that adequate resources be available for managing and responding to a particular project risk.

- What is risk monitoring and control?

Once the risk response plan is created, the various risk triggers must be continually monitored to keep track of the various IT project risks. In addition, new threats and opportunities may present themselves over the course of the project, so it is important that the project stakeholders be vigilant. Risk monitoring and control should be part of the overall monitoring and control of the project. Monitoring and control focus on metrics to help identify when a risk occurs, and also on communication. (p. 203)

- Describe the three risk monitoring tools that were discussed in this chapter.

- Risk Audits—The audit should focus on ensuring that the project manager and team have done a good job of identifying and analyzing project risks and on ensuring that proper procedures and processes are in place. Risk audits should be conducted by people outside the project team. Using outsiders provides a fresh perspective; the project team may be too close to the project and miss significant threats or opportunities.

- Risk Reviews—Risk audits should be conducted by individuals outside the project team; but risk reviews can be conducted internally. Throughout the project life cycle, the project stakeholders should hold scheduled, periodic risk reviews. These reviews should be part of each team meeting and part of the project team’s learning cycles.

- Risk Status Meetings and Reports—Similar to risk reviews, a monitoring and control system should provide a formal communication system for monitoring and controlling project risks.

- What is the purpose of evaluating a response to a particular risk?

The outcome of the risk response will either be favorable or unfavorable. Therefore, a great deal can be learned about the entire process of risk management (i.e., the preparedness of risk planning, identifying risks, analyzing and assessing risks, risk responses, and so forth). Lessons learned can lead to the identification of best practices that can be shared throughout the project organization. In summary, lessons learned and best practices help us to:

- Increase our understanding of IT project risk in general.

- Understand what information was available to managing risks and for making risk-related decisions.

- Understand how and why a particular decision was made.

- Understand the implications not only of the risks but also the decisions that were made.

- Learn from our experience so that others may not have to repeat our mistakes.

Essay Questions

1.	The text discusses three common mistakes found in managing project risk. Choose two of them and after stating them, discuss the implications of making that mistake.

2	What should be required of project stakeholders with regard to managing project risk successfully?

3.	Briefly describe the seven IT Project Risk Management processes.

4.	Compare the three types of project risk: known, known-unknown, and unknown-unknown. Give an example of each.

5.	What are the strengths and weaknesses of using the Delphi Technique for identifying threats and opportunities?

6.	What are the potential advantages that qualitative approaches have over quantitative ones when it comes to risk analysis and assessment?

7.	Describe each of Tusler’s four quadrant-menagerie of risk classification.

8.	How is a Monte Carlo simulation conducted?

9.	What factors determine the appropriate risk strategy to deploy?

10.	The text discusses four main risk response strategies. Briefly describe them and the implications of choosing one over another.

11.	Describe some of the tools that are typically employed to monitor and control risk.